## Sheet1
Use Case | Use Case Name | Effort (People*Weeks) | Iteration 2* (03/31/20) | Iteration 3* (05/05/20)
UC 1 | Register | 1 | 1
UC 2 | Login | 1 | 1
UC 3 | Logout | 1 | 1
UC 4 | View Profile | 1 | 1
UC 5 | Update Profile | 1 | 1
UC 6 | View Cart(s) | 1 | 1
UC 7 | View Truck(s) | 1 | 1
UC 8 | View Items | 1 | 1
UC 9 | My Order | 1 | 1
UC 10 | Payment | 1 | 1
UC 11 | Receipt | 1 | 1
UC 12 | Cancel Order | 1 | 1
UC 13 | Order History | 1 | 1
UC 14 | View Vehicles | 1 | 1
UC 15 | Item Inventory | 1 | 1
UC 16 | Assign shift | 1 |  | 1
UC 17 | vehicle schedule | 1 |  | 1
UC 18 | Operator schedule | 1 |  | 1
UC 19 | Total Revenue | 1 |  | 1
UC 20 | Shift Details | 1 |  | 1
UC 21 | Vehicle Inventory | 1 |  | 1
UC 22 | Vehicle Revenue | 1 |  | 1
UC 23 | Picked-up order | 1 |  | 1
| Total Effort Estimated |  | 15 | 8
| Total Effort Available |  | 30 | 30
|  | Team Size | 6
Note on D29: Robb: Enter team size here